## Feuille1
Actions Management

I ] Supervisor Meetings related Actions
ID	Origine	Description	In charge	Due date	closing date	State
I.1	Réu 15/01	minutes redaction	X. Méchin	D + 1	15/01/15	Closed
I.2	Réu 22/01	minutes redaction	P-L Michel	D + 1	22/01/15	Closed
I.3	Réu 28/01	minutes redaction	É. Lebrun	D + 1	28/01/15	Closed
I.4	Réu 10/02	minutes redaction	K. Auguste	D + 1	10/02/15	Closed
I.5	Réu 25/02	minutes redaction	M. Arthaud	D + 1	25/02/15	Closed
I.6	Réu 04/03	minutes redaction	K. Auguste	D + 1	04/03/15	Closed
I.7	Réu 10/03	minutes redaction		D + 1

II ] Other Actions
II.1	Needed to start modifications	Initialise the repo with CRAPS sources	M. Arthaud	22/01/15	22/01/15	Closed
II.2	Needed to start modifications	Install a working Virtual Machine	M. Arthaud	22/01/15	22/01/15	Closed
II.4	Needed to work in parralel	Get 4 more Nexys cards	M. Carton	30/01/15	30/01/15	Closed
II.5	We haven't seen P L for a week	Try to reach Pierre Louis / get info	M. Carton	Asap	10/02/15	Closed
II.6	End of 1st VM' s validity	Install a new VM	M. Arthaud	22/02/15	18/02/15	Closed
II.7	Client Meeting	Evaluate difficulty for Nexys 4 adaptation	M. Carton	13/03/15	09/03/15	Closed